## Code Sharks Project Backlog
PROJECT BACKLOG
Work item | Type | Description | Priority | Effort
Milestone 1 | Epic | As a client, I can understand the Project details, values, and deadlines through the Business Requirement Document, Project Plan, and High Level Design | 1 | 39
Project Proposal | User Story | As a developer, I would like to see the values and features of the product | 1 | 16.5
PP Features | Split Story | As a developer, I want to know what features will connect with the value | 1.1 | 3
PP User Needs | Split Story | As a developer, I want to know who the target audience is | 1.2 | 2
PP Proposed Solution | Split Story | As a developer, I want to know how the product will fix the problem | 1.3 | 2
PP Future Vision | Split Story | As a developer, I want to know the possible scalability of the product | 1.4 | 2
PP Product Scope | Split Story | As a developer, I want to know the complexity of the product | 1.45 | 1.5
PP Project Scope | Split Story | As a developer, I want to know the complexity of the project | 1.5 | 1.5
PP About Project | Split Story | As a developer, I want to know what the product is | 1.6 | 1
PP Abstract | Split Story | As a developer, I would like to get a summary of the product | 1.65 | 1
PP Competitors | Split Story | As a developer, I would like to know who has created a similar product and if they are successful | 1.7 | 1
PP References | Split Story | As a developer, I would like to see the references for information | 1.8 | 0.5
PP Glossary | Split Story | As a developer, I would like to see the meaning of words to understand the same language | 1.9 | 1
Business Req. Document | User Story | As a client, I would like to see the FRQs, NFRQs, and Business Rules | 2 | 14
BRD Use Cases | Split Story | As a client, I want to understand the function and non-functional requirements for the features | 2.1 | 3
BRD Business Requirements | Split Story | As a client, I want to understand the business requirements | 2.2 | 3
BRD Glossary | Split Story | As a client, I want to understand the text using the same language | 2.3 | 2
BRD Document Resouces | Split Story | As a client, I want to identify all stakeholders involved with the project | 2.4 | 2
BRD Project Overview | Split Story | As a client, I want to understand the product from the developer's POV | 2.5 | 2
BRD Overview | Split Story | As a client, I want to understand what is inside the document | 2.6 | 2
Project Plan | User Story | As a client, I would like to see the roadmap and dates of features | 3 | 15
High Level Design | User Story | As a developer, I can understand the significance of each features and how they work with everything else | 4 | 10

## CodeSharks Sprint 1
Andrew De La Rosa |  | Don't change this column
Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 8 | CodeSharks
0 | 0 | 8 |  |  | Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 31
1 | 1 | 7 |  |  | 0 | 2 | 31
2 | 2 | 5 |  |  | 1 | 4 | 27
3 | 2 | 3 |  |  | 2 | 8 | 19
4 | 3 | 0 |  |  | 3 | 6 | 13
5 | 0 | 0 |  |  | 4 | 5 | 8
[5 empty] | 5 | 1 | 7
David Chan
Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 10
0 | 2 | 10
1 | 1 | 8
2 | 4 | 4
3 | 1 | 3
4 | 0 | 3
5 | 0 | 3
Bryant Lam
Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 8
0 | 0 | 8
1 | 1 | 7
2 | 2 | 5
3 | 2 | 3
4 | 1 | 2
5 | 0 | 2
Sean Iida
Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 5
0 | 0 | 5
1 | 1 | 4
2 | 0 | 4
3 | 1 | 3
4 | 1 | 2
5 | 1 | 1
Joshua Hicks
Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 0 | 0
1 | 0 | 0
2 | 0 | 0
3 | 0 | 0
4 | 0 | 0
5 | 0 | 0

## CodeSharks Sprint 2
Andrew De La Rosa |  | Don't change this column
Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 10 | CodeSharks
0 | 0 | 10 |  |  | Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 30
1 | 2 | 8 |  |  | 0 | 0 | 30
2 | 2 | 6 |  |  | 1 | 4 | 26
3 | 1 | 5 |  |  | 2 | 5 | 21
4 | 0 | 5 |  |  | 3 | 2 | 19
5 | 0 | 5 |  |  | 4 | 0 | 19
6 | 0 | 5 |  |  | 5 | 0 | 19
7 | 0 | 5 |  |  | 6 | 0 | 19
[5 empty] | 7 | 0 | 19
David Chan
Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 0 | 0
1 | 0 | 0
2 | 0 | 0
3 | 0 | 0
4 | 0 | 0
5 | 0 | 0
6 | 0 | 0
7 | 0 | 0
Bryant Lam
Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 10
0 | 0 | 10
1 | 1 | 9
2 | 2 | 7
3 | 1 | 6
4 | 0 | 6
5 | 0 | 6
6 | 0 | 6
7 | 0 | 6
Sean Iida
Sprint Length(Days) | Hours of Productivity | Remaining Work | Time of Tasks: | 10
0 | 0 | 10
1 | 1 | 9
2 | 1 | 8
3 | 0 | 8
4 | 0 | 8
5 | 0 | 8
6 | 0 | 8
7 | 0 | 8

## CodeSharks Daily Stand-ups
Daily Stand-ups Sprint 1
2022-09-20 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew | No | Researched and helped think of features for the RFP | I am going to continue to think of features for our RFP
David | No | I started second version of the RFP and created an outline for it along with some new features. | I am adding more features into RFP and will create the project the project scope and software sections
Bryant | No | Researched examples of BRDs | I will create the Project Backlog and work on Project Proposal Features
Sean | No |  | Brainstorm more features and update the Project Proposal
Joshua
2022-09-21 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew | No | I helped create new feature ideas for the RFP | I am going to work on the PP Future Vision and PP Features, as well as look over my teammates work and give feedback
David | No | I added more features into RFP and created project scope and software sections | I am going to research features and work on PP Features
Bryant | No | I created the Project Backlog and worked on Project Proposal Features | I am going to work on the PP Competitors and PP User Needs
Sean |  | Came up with more features and updated project proposal | Implement some features into rfp
Joshua
2022-09-22 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew | No | I worked on the PP Future Vision and PP Features | I am going to work on PP Glossary and PP Features again, as well as cleanup document
David | No | I added new features and edited other features to fit a theme. | I am working on PP Abstract and PP Proposed Solution.
Bryant | No | I completed the PP User Needs and worked on PP Competitors | I am going to continue working on PP Competitors and create the BRD Framework/Template
Sean | No | Added to rfp unique features
Joshua
2022-09-23 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew | No | I completed the PP Glossary and PP Features
David | No | I completed PP Abstract and PP Proposed Solution. | I am working on researching new ideas for features.
Bryant | No | I completed PP Competitors and worked on the BRD Framework/Template | I am going to complete the BRD Template and work on BRD Overview
Sean | No |  | Tweak use case format
Joshua
2022-09-24 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew
David | No | I thought of 3 new ideas of playdates, puppy growth collage, and to improve pet profile with medical records. | I am going to implement the new ideas and edit other features to align better with our value.
Bryant
Sean | No | fixed the formatting of our brd usecases | Work on BRD use cases
Joshua
Daily Stand-ups Sprint 2
2022-09-26 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew | No |  | I will be assisting with fixing the PP features
David | No | I did not do anything yesterday. | I will be attempting to fix the product features of the RFP.
Bryant | No |  | I am going to refine PP Features.
Sean | no
2022-09-27 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew | No | I helped fix the Pet Profiles, as well other gramatical and other similar errors.
David | No | I fixed the features for interactive petcam, pet sitting services, pet care services, and I also did a small part of future plans. | I will change how pet profiles and playdate will work and will add more future plans
Bryant | No | I worked on PP Features | I will add more features to PP Features
Sean | no |  | Working on outine of hl design doc
2022-09-28 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew | No |  | I will work on BRD Use Cases
David | No | I changed how pet profile and playdate works and added future plans improvement to playdate, livechat reactive sounds, and pet profiles. | I will review and edit the RFP to get it ready to submit the version 3 for approval.
Bryant | No | I worked on PP Features | I will work on BRD Use Cases
Sean | No | Worked on HL Design Document | Same as yesterday
2022-09-29 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew
David
Bryant
Sean
2022-09-30 | Are you blocked? | What did you do yesterday? | What are you going to do today
Andrew
David
Bryant
Sean